## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a user, I want to create an account so that I can securely access the AI Decision Hub. | MUST HAVE | Database, Authentication | Team Member 1 | 3- Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want to log in securely so that I can access my conversations and decisions. | MUST HAVE | Authentication | Team Member 2 | 3- Completed
Sprint 1 | Sprint 1 | US03 | As a user, I want to submit a decision-related query so that the system can analyze it. | MUST HAVE | Backend API | Team Member 3 | 3- Completed
Sprint 1 | Sprint 1 | US04 | As a user, I want the Coordinator Agent to identify the tasks required for my query. | MUST HAVE | LLM, Agent Workflow | Team Member 4 | 3- Completed
Sprint 1 | Sprint 1 | US05 | As a user, I want specialized agents to perform different tasks such as research, analysis and decision making. | MUST HAVE | analysis and decision making. | Team Member 5 | 3- Completed
Sprint 1 | Sprint 1 | US06 | As a user, I want agents to share information through a common workflow state. | MUST HAVE | Agent Workflow | Team Member 6 | 3- Completed
Sprint 1 | Sprint 1 | US07 | As a user, I want the system to use external tools when required to solve my query. | MUST HAVE | Tool APIs | Team Member 7 | 3- Completed
Sprint 1 | Sprint 1 | US07 | As a user, I want my previous conversations to be stored so that I can access them later. | MUST HAVE | Database | Team Member 7 | 3- Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want to generate a final recommendation based on the information collected by the agents. | MUST HAVE | Analysis Agent, Decision Agent | Team Member 2 | 3- Completed
Sprint 1 | Sprint 1 | US03 | As an administrator, I want to monitor agent executions, failures and response times. | MUST HAVE | Logging, Database | Team Member 3 | 3- Completed
Sprint 1 | Sprint 1 | US01 | As a user, I want a responsive web interface for interacting with the AI Decision Hub. | MUST HAVE | React/HTML/CSS/JS | Team Member 1 | 3- Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want the application to be deployed so that it can be accessed remotely. | MUST HAVE | Deployment | Team Member 2 | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Design and prototypes | 2026-07-15 | 2026-07-18 | Team Member 1 | Design | 3- Completed
US02 | T02 | Development of frontend | 2026-07-20 | 2026-07-02 | Team Member 2 | Coding | 3- Completed
US03 | T03 | Development of backend | 2026-08-04 | 2026-08-12 | Team Member 3 | Coding | 3- Completed
US04 | T04 | Orchasteration of Agents | 12--08-2026 | 2026-08-16 | Team Member 4 | Integration Test | 3- Completed
US05 | T05 | Testin of System | 2026-08-18 | 2026-08-24 | Team Member 5 | System Test | 3- Completed
US06 | T06 | Deployment | 2026-08-26 | Others | 3- Completed | Others | 3- Completed
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty deciding responsibilities of individual agents. | Defined responsibilities for Coordinator, Planning, Research, Analysis and Decision agents.
Sprint 1 | Day 2 | Agent workflow was not passing information correctly between stages | Updated shared state structure and tested state transitions.
Sprint 1 | Day 3 | Healthcare API returned inconsistent results for some locations. | Added input validation and improved API request handling.
Sprint 1 | Day 4 | Frontend was not communicating with backend correctly. | Configured API endpoints and CORS settings.
Sprint 1 | Day 5 | Authentication errors occurred during API requests. | Fixed token handling and protected API endpoints.
Sprint 1 | Day 6 | Deployment configuration issues. | Updated environment variables and deployment configuration.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-15 | 2026-07-17 | Team Member 1 | Start testing authentication earlier. | Stop waiting until the end to integrate frontend and backend. | Continue maintaining clear API contracts. | Added authentication test cases before integration.
2 | Sprint 1 | 2026-07-19 | 2026-07-22 | Team Member 2 | Start documenting agent responsibilities before implementation | Stop changing agent responsibilities frequently. | Continue testing Coordinator routing. | Created agent responsibility documentation.
3 | Sprint 1 | 2026-07-25 | 2026-07-28 | Team Member 3 | Start testing shared state after every workflow stage. | Stop relying only on final output for debugging | Continue modular agent development | Added state validation after agent execution.
4 | Sprint 1 | 2026-07-29 | 2026-08-03 | Team Member 4 | Start testing external APIs with failure cases. | Stop assuming APIs will always respond successfully. | Continue integrating reusable tools. | Added timeout and error handling.
5 | Sprint 1 | 2026-08-04 | 2026-08-12 | Team Member 5 | Start integrating UI with backend earlier. | Stop developing frontend independently for too long. | Continue improving usability. | Connected major UI components to backend APIs
6 | Sprint 1 | 2026-08-15 | 2026-08-21 | Team Member 6 | Start tracking agent execution metrics earlier. | Stop relying only on console logs. | Continue working on monitoring. | Connected major UI components to backend APIs
7 | Sprint 1 | 2026-08-23 | 2026-09-01 | Team Member 7 | Start deployment testing before the final stage. | Stop treating deployment as a last-minute activity. | Continue maintaining backend stability. | Created deployment checklist and tested environment configuration.