## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DE-1 | team member 1 | 2026-07-16 | Authentication Issue | Sprint 1 | team Member 2 | User Interface | Solved the issue using Jwt token | 2026-07-19 | closed | Nothings evrything is smooth
DE-2 | team member 2 | 2026-07-23 | Logic Bug in the workflow | Sprint 1 | team member3 | Logical | Solved by solid discussion | 2026-07-30 | closed | Good
DE-3 | tea member 3 | 2026-08-02 | Agent conflict | Sprint 1 | team 1 | Standards | Structured the agent and give a standard data | 2026-08-05 | closed | Smoothly run
DE-4 | team member 4 | 2026-08-10 | report generation network trouble | Sprint 1 | team 4 | Maintainability | use the stable model to rectify the issue | 2026-08-12 | closed | valid connection
DE-5 | team member 5 | 2026-08-20 | Deployment failure | Sprint 1 | team 6 | Standards | Optimize the code and use a best and minimize the model for effective symtoms checker | 2026-08-25 | closed | Smoothd deployement and stable pinging

## Sheet2
Logical
User Interface
Maintainability
Standards
Others